## Slide 1
MGT / BUILD REVIEW
MGT Skin Care v2
Build status and production launch plan
Local build validated.
Production release still gated.
September 9, 2026 • Planning estimate: 4–6 weeks for a referral-portal launch
Notes: Audit of local source and tests, September 8–9, 2026. Sites get_site: current_live_url=null, latest_version_number=0. Timeline is an engineering estimate, not a deployment commitment.

## Slide 2
Release readiness
A functional local preview with unresolved production dependencies
Area | Current position | Release implication
Frontend and API | Local builds and suites pass | Connected workflows are ready for staging validation.
Production services | No published Sites version | Hosting, PostgreSQL and live sign-in need setup and testing.
Content and operations | Approval and privacy gaps | Launch needs reviewed content, policies and operational owners.
Shipping estimate | 4–6 weeks, conditional | Target Oct 7–21 if dedicated work starts Sep 9.
02
Notes: Sources: work/release-verification.log, CURRENT-SCOPE.md, infra/portal/README.md, Sites project appgprj_6a9cb9f6a1e08191af5409cd113f054c. Dates are derived estimates.

## Slide 3
Customer journeys
The existing dark theme, violet accents and page structure are preserved
Journey | Implemented locally | Limits at launch
Shop and Saved | 11 retailers, 7 segments, compare 3 | Download, restore links and save shortlist. Retailers own price and stock.
Beauty & Style | Six preference-based sections | Save, remove and detect stale edits. No photo or live AI assessment.
Skin Match and Routine | Profile, exclusions and rules | Production matching needs approved product and ingredient records.
Account and Support | Export, requests and admin replies | Sign-in needs live validation. Replies stay within the portal.
03
Notes: Sources: apps/api/src/portal/retailers.ts, style.ts, server.ts, catalog.ts; apps/web/src/components/RetailerDirectory.tsx, RetailerComparison.tsx, BeautyStudio.tsx. Retailer directory presence is not a partnership certification.

## Slide 4
This build closes an admin access gap
Content review roles no longer receive customer operations records
Role | Content records | Operational records
Guest / customer | Admin access denied | Admin access denied
Viewer / editor / SME | Products, rules and knowledge | Support, orders, jobs, audit and deletion requests withheld
Compliance / superadmin | Products, rules and knowledge | Operational access retained
Role revoked | Rechecked on the next request | Existing session immediately loses operations access
The admin screen now explains restricted access. Tests cover forged headers and denied writes.
04
Notes: Changed apps/api/src/portal/server.ts /admin and apps/web/src/components/ConnectedAdmin.tsx. Added apps/api/test/admin-access.cjs: seven role combinations, guest/customer denial, filtering, forged headers, denied writes, live revocation. Local test accounts only.

## Slide 5
Backend and security
Core protections exist, but the production environment is unproven
Implemented
Cookie sessions, CSRF and origin checks
Server-side roles and record ownership
Referral-only gates block legacy product checkout, refunds and payouts
Still required
Live email sign-in and session lifecycle tests
Production PostgreSQL integration and load checks
Security review, dependency review and verified operational access
05
Notes: Sources: apps/api/src/portal/security.ts, server.ts, store.ts, portal.cjs, admin-access.cjs. Production startup rejects SQLite, demo mode and HTTP public origins. This audit is not a penetration test.

## Slide 6
Data and privacy
Storage and consent flows are connected; lifecycle operations remain incomplete
Capability | Current state | Required before release
Storage | SQLite locally, PostgreSQL adapter | Exercise production database, migrations and concurrency.
User controls | Consent, export and style removal | Validate real account ownership and supported deletion scope.
Account deletion | Request is stored as pending | Implement and test execution, retention and provider cleanup.
Recovery | Deployment notes describe backups | Install backup jobs and prove restore plus rollback.
06
Notes: Sources: server.ts /account/export and /account/deletion-request (30-day not_before), style.ts /style-profile/remove, store.ts and infra/portal/README.md. No automated retention/deletion/backup jobs verified.

## Slide 7
AI, matching and editorial content
These capabilities require approved inputs as well as working code
Implemented
Coach selects reviewed library excerpts and rejects unsupported quotations
Matching rules and sample pipeline have local coverage
Editorial drafting and second-reviewer approval routes exist
Release gates
Approve real product, ingredient and knowledge records
Configure and test live providers, timeouts and failure states
Review actual responses for safety and usefulness before enabling AI
The running preview reports AI unconfigured. Unready features need explicit disabled or unavailable states.
07
Notes: Sources: apps/api/src/portal/ai.ts, catalog.ts, server.ts; test/coach.cjs; packages/domain/src/__smoke__/pipeline.ts. GET /api/hub/session during this audit: ai_configured=false, demo=false. No live provider assessment was performed.

## Slide 8
Subscriptions and excluded scope
Billing is optional for the first referral-portal release
Area | Prepared in code | Remaining / excluded
Consumer and vendor plans | Separate audiences and billing records | Prices, benefits, terms and live Stripe setup remain pending.
Trial and billing cycles | 14-day trial, monthly and annual paths | Verify trial-to-paid, renewals and cancellation in Stripe sandbox.
Payment safeguards | Signed events and mocked lifecycle tests | Live reconciliation, recovery and operational monitoring needed.
Product commerce / mobile | Commerce blocked. Mobile scaffold only. | No direct checkout or app-store release in this launch estimate.
08
Notes: Sources: apps/api/src/portal/billing.ts, test/billing.cjs, infra/portal/README.md, apps/mobile. Stripe tests use a mock client with real signature validation, not a live Stripe account. Product purchases stay at external retailers.

## Slide 9
Hosting and source delivery
Source backups exist. Production deployment and release automation are pending.
Layer | Evidence | Next requirement
Sites publication | No live URL, version count 0 | Choose and validate a compatible production runtime.
Deployment scaffold | Next.js, Express, PostgreSQL, Caddy | Container build, HTTPS, secrets and staging exercise.
GitHub saving | Full source ZIP checkpoints | Publish an extracted source tree before CI can run on source.
Google Drive saving | Snapshot archive folder established | Continue versioned source and report backups.
This build corrects the API image’s missing build-script reference and excludes more local caches.
09
Notes: Sources: .openai/hosting.json, Sites get_site, infra/portal/Dockerfile.api, Dockerfile.web, compose.yaml, .dockerignore, BUILD-CHECKPOINTS.md. Existing public GitHub repository stores source ZIPs. No container build performed; Docker/psql executables were unavailable on this host.

## Slide 10
Validation completed
One release-check command now runs the complete local verification set
Check group | Result | Evidence boundary
Build and types | 5 passed | Domain, shared, AI gateway types, API and production web build.
API suites | 5 passed | Referral, billing, coach, style and new admin access coverage.
Domain / gateway suites | 3 passed | Rules pipeline, mocked provider routing and pricing logic.
Web suites | 4 passed | Rendering, admin rendering, shop links and client recovery.
Local HTTP checks also pass. Browser E2E, live services, containers and production load remain unverified.
10
Notes: Command: pnpm verify:release. Evidence: work/release-verification.log. Rendering suites include earlier components and do not establish full current-page browser coverage. Local HTTP /shop and proxied /api/hub/retailers returned 200; /readyz returned ok, storage sqlite.

## Slide 11
Launch blockers and accountable roles
Roles below are proposed responsibilities, not assigned people
Gate | Required outcome | Accountable role
Source and hosting | Source checkout, staging, HTTPS and secrets | Engineering + operations
Accounts and privacy | Live sign-in, deletion and retention execution | Engineering + privacy reviewer
Content and business | Approved data, company identity and policies | Product owner + editorial reviewer
Quality and recovery | Browser QA, restore test, monitoring and pilot | QA + operations + product owner
Billing and AI have additional gates if included in the launch scope.
11
Notes: Derived backlog from CURRENT-SCOPE.md, infra/portal/README.md, current code inspection and audit results. Named owners and credentials have not been assigned by the user. Legal/policy readiness is a project gate, not legal advice.

## Slide 12
Production timeline
Illustrative schedule from September 9, subject to the gates being met
Window | Work | Exit evidence
Week 1 • Sep 9–15 | Freeze scope, source checkout, staging setup | Hosted staging plan and accountable owners.
Week 2 • Sep 16–22 | Auth, privacy jobs, data and policy review | Live account journey and deletion demonstration.
Weeks 3–4 • Sep 23–Oct 6 | Integration, browser QA, recovery and pilot | Acceptance journeys and restore exercise pass.
Weeks 5–6 • Oct 7–21 | Resolve pilot issues and release gradually | Go/no-go approval, monitoring and rollback ready.
Assumes one dedicated full-stack engineer plus part-time QA/operations and prompt owner reviews.
12
Notes: Engineering planning estimate, not a promise. Assumes credentials/domain available in week 1, decisions within two business days, no major redesign, web referral scope, AI/billing disabled unless separately accepted. Delayed dependencies move the calendar. Four to six weeks from Sep 9 yields Oct 7–21.

## Slide 13
Production acceptance criteria
Passing local tests is one gate in the release decision
Customer and privacy acceptance
Shop → compare → save → restore works on desktop and mobile browsers
Real sign-in, logout and account isolation pass
Export, deletion and retention are demonstrated
Operational acceptance
Production database and HTTPS staging are verified
Backups restore successfully and rollback is rehearsed
Monitoring, support ownership and a small-user pilot are ready
No unresolved critical security defects. AI or billing must pass their own live-service checks before activation.
13
Notes: Proposed launch acceptance criteria from audit findings. Browser accessibility, keyboard use, responsive layouts and error states belong in QA. These acceptance outcomes have not yet been completed.

## Slide 14
Scope assumptions and next work
The schedule protects the referral-portal scope already established
Next engineering work
Set up a real source checkout and staging release process
Implement account deletion and retention execution
Validate PostgreSQL, live email sign-in and browser journeys
Owner inputs
Confirm launch audience, domain and support owner
Approve company identity, policies and content reviewers
Decide whether AI and subscriptions join the first release
Including live AI and billing adds an estimated 2–4 weeks after their inputs are ready. Mobile and direct commerce need separate plans.
14
Notes: Estimate assumes no architecture redesign or direct product commerce. Additional AI/billing validation range is a planning estimate and cannot be scheduled until provider configuration, prices/benefits and approved content are ready. No purchasing, live billing activation or production deployment performed.

## Slide 15
Audit sources and limitations
Status is grounded in the current local build, not a completion percentage
Primary evidence
Source: API portal, web components, domain and gateway packages
Deployment: infra/portal and .openai/hosting.json
Checks: pnpm verify:release and local HTTP responses
What this review does not prove
No live Supabase, Stripe or AI provider verification
No production PostgreSQL, container, load or full browser E2E run
No published production version or operational recovery exercise
Detailed status, risks and the launch plan accompany the source checkpoint. Audit completed September 9, 2026.
15
Notes: Detailed evidence and timeline assumptions are preserved in PRODUCTION-STATUS-2026-09-09.md. Latest pre-audit local commit b90d6b2; this checkpoint adds admin filtering and release verification. GitHub source ZIPs are backups, not executable CI source checkouts.